**Primary Physical Education and Sport Premium Funding Action Plan**



**Kingsfield First School 2020-21**

**What is the PE and Sports Premium Funding?**

The government is providing funding of over £450 million per annum for academic years 2013-2020 to provide new, substantial primary school sport funding. This funding is being jointly provided by the Departments for education, Health and Culture, Media and Sport and will see money going directly to primary school head teachers to spend on improving the quality of sport and PE for all their children.

The sport funding can only be spent on sport and PE provision in schools.

**Purpose of funding**

Schools have to spend the sport funding on improving provision of PE and sport but they will have the freedom to choose how they do this.

The vision for the Primary PE and Sport Premium**: ALL** pupils leaving primary school **physically literate** and with the **knowledge, skills and motivation** necessary to equip them for a **healthy, active lifestyle** and **lifelong participation** in physical activity and sport

The funding has been provided to ensure impact against the following **OBJECTIVE:** To achieve self-sustaining improvement in the quality of PE and sport in primary schools. It is important to emphasise that the focus of spending must lead to long lasting impact against the vision that will live on well beyond the Primary PE and Sport Premium funding.   
  
**It is expected that schools will see an improvement against the following 5 key indicators:**

**Key Indicator 1: the engagement of all pupils in regular physical activity - the Chief Medical Officer guidelines recommend that all children and young people aged 5 to 18 engage in at least 60 minutes of physical activity a day, of which 30 minutes should be in school**

**Key Indicator 2: the profile of PE and sport is raised across the school as a tool for whole-school improvement**

**Key Indicator 3: increased confidence, knowledge and skills of all staff in teaching PE and sport**

**Key Indicator 4: broader experience of a range of sports and activities offered to all pupils**

**Key Indicator 5: increased participation in competitive sport**

Here at Kingsfield First School we value the difference physical education and sport can have on children’s lives and we work hard to embrace all the opportunities we can to give pupils access to as many sporting experiences as possible. In addition to this we advocate and use the outdoor environment as much as possible to add value to the curriculum our pupils receive.

**KINGSFIELD FIRST SCHOOL**

**Primary Physical Education and Sport Funding Action Plan**

**2019-2020**

**Amount of Grant Received** – Year:- 2019-2020 £17,80 0

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Area of Focus** | **Evidence of need**  (Why we are doing it) | **Action Plan** | **Who** | **Time Scale** | **Funding**  **Breakdown** | Impact and Evidence record |
| **Curriculum**  **Key Indicator 1** |  |  |  |  |  |  |
|  | To see how children are getting to school and increase healthier choices in how to get to school | Monitor how children are traveling to school | KP | Spring 21 | £0 | **Children are aware of how to live a healthy lifestyle in and out of school.** |
|  | To encourage healthy means of getting to schools | Invest in a bike rack to encourage children to bring their bikes to school | KP | Summer 21 | £300 | **An increase of children are coming to school on their bike and are making healthy choices.** |
|  | To engage children in to different sports | Plan and deliver an active healthy sports week where connections to the local clubs are established | KP | Summer 2021 | £0 | Children’s awareness and love of a range of sports is increased |
|  | To help EYFS in their physical development | Invest in an EYFS play area to assist in physical development and aid in the outdoor provision | KP | Summer 21 | £15,000 | Children able to practice physical development in fun and interactive environment.  January 2021 – meeting scheduled |
|  | To engage and ensure all children are participating in PE | Provide PE kits to allow all children to access their PE lesson. | KP | Summer | £100 | 100% of children will participate in PE lessons. |
|  | To engage and ensure all children are participating in PE | Invest in playground (covid safe) equipment to encourage children to be active during their playtime. | KP | Autumn 2020 | £500 | More children are active at lunchtime. |
|  | To motive children to be more active during playtimes | Invest in the multi shoot to encourage children to be active during playtime and lunch time. | KP | Summer 2021 | £2500 | Children more active during break times and lunch times. |
|  | To motivate children into being active for 60 minutes per day | Place 9 things to do on newsletter and homework menus to promote healthy living at home | All staff ND | Aut 2020 | £0 | Children and parents are aware of how to participate in a healthier lifestyle outside of school.  January update – before lockdown was on news letter |
| **Key Indicator 2** |  |  |  |  |  |  |
|  | To enable all children to participate in lessons. | Invest in curriculum equipment to encourage children to be active during their lessons | KP and sports champions | Spring  2021 | £400 | 100% of PE lessons are fully equipped |
|  | To allow lessons to be more active | Invest and liaise with consultant for an orienteering trail to be fitted to encourage more active lessons. | Consultant | Spring 2021 | £800 | Staff utilise outdoors regularly and appropriately. Raising the profile of the outdoor and adventurous element of PE.  January update – contact made with provider and possible zoom training being planned. |
|  | To allow children to be independent and autonomous in their learning and critique performances | Invest in a Ipad locker to ensure the IPads which are used specifically for PE are safe. |  | Spring 2021 | £500 | iPads are safe used well and pupils have regular opportunities to evaluate their performances. They do so with increasing maturity, accuracy and knowledge  January update: ipad locker has been ordered.  . |
|  | To ensure equipment is safe, secure and easily accessible | To invest in containers to keep equipment safe and secure. | Mick | Spring 2021 | £1600 | **PE equipment is stored safely and securely which as a result prolongs the durability of the equipment.** |
|  | To raise profile of PE | To laisse with consultant in gaining the YTS mark to raise the profile of PE  To maintain the silver sports mark | KP | Summer 2021 | £0 | **Profile of PE continues to be raised and achievements are acknowledged by gaining an OFSTED recognised quality mark.** |
|  | Summer 2021 | £0 |
|  | To ensure teaching is progressive throughout the school | To roll out curriculum progression, unit and lesson pathways and vocabulary and to ensure all staff are following this. | KP | Autumn 20 and Spring 21 | £0 | Progression of skills are clear throughout all PE lessons and children understand the pathways for each lesson and unit.  January update: Pathway and progression have been rolled out and monitoring in Dec indicates that staff and pupils are following it. |
| **Key Indicator 3** |  |  |  |  |  |  |
|  | To be up to date with all risk assessments involving PE | To attend the health and safety course and obtain the new health and safety regulations. | KP and consultant | Aut 20 | £95 | All staff are up to date with the current health and safety and ensure that this is being followed in all lessons.  January update: KP attended online course and new health and safety book in school |
|  | Further developments required to develop our PE curriculum- subject leadership evaluation findings. | Attend Network Meetings | KP | All year | £250+ | PE lead will be up to date on correct and current PE legislation, clarity with intent, implementation and impact.  January update : KP attending network meetings with the next 27th Jan |
|  | Missing training from previous year due to maternity leave. | LS and AC to attend games which will improve their confidence and ability of teach across the area of games, dance and gym. | AC and LS | Sum 20 | £0 | 100% Staff are more confident in delivery of Games, Dance and Gym lessons  100% of Games lessons are good and pupils all making good progress in lessons  100% of staff from staff questionnaire found training useful |
| **Key Indicator 4** |  |  |  |  |  |  |
|  | To raise the profile of PE through affiliation of professional clubs. | Establish at least termly contact with professional organisations- swimming club, professional football clubs/players, Tennis via the LTA, Congleton Tag rugby, Congleton golf, chance 2 shine. | KP | Aut 20 - ongoing | £0 | Good links evident- taster sessions offered where appropriate  Sign posting offered to relevant pupils/parents |
| **Competition**  **Key Indicator 5** |  |  |  |  |  |  |
|  | To increase the number of competitive opportunities for pupils.  Recognition of some children’s successes in sport outside of school  Increase participation in competitive sport. | Calendar of sporting events put together throughout the year for Y1 – Y4 pupils including competitions to engage all local Biddulph Schools. Activities to include Tag ruby, Netball, quick sticks. Coaches funded for the transport of children | KP | Through year | Travel £ 570 | – Baseline calendar of competitions. Children are being exposed to the element of competition, this includes  January update: Network meeting with Biddulph Schools was completed and some competitions planned. However due to lockdown these have not been able to run currently. |
|  | Inter–school competitions planned between the Federated schools. | KP | Ongoing | £0 | – All staff aware of the events particularly during healthy sports week where sport champions organise and lead for others. |
|  | Intra-school competitions planned within the school | KP | Throughout the year |  |  |
|  | Pupils to perform at Inspire Dance Competition led by High school dance leaders | KP | Spring 21 | £0 | Pupils attend inspire dance club and perform in Feb 2021- enjoyment levels are high  January update: Due to covid this was changed to in lessons teaching of the dance and was scheduled to be filmed and shared with Biddulph Schools, still waiting on BHS to film due to absences. |
|  | KP to attend creating a buzz around the Olympics and liase with other Pe leaders to arrange MAT Olympics for 3/4 | KP | Summer 2021 | £150 | Profile of Olympics is raised through intra and inter school competitions.  January update: Booked |
|  |  |  |  |  |  | **Evidence:** Lesson observations, planning documents, Learning walks, Staff feedback, PE action plan, PE lead performance management document.  **Sustainability**: Staff increased knowledge for future years.PE subject lead competency to strategically continue moving the school forward in terms of PE. House leaders in every class available to support colleagues to continue to move practice forward and model lessons/ team teach as needed. |
|  |  |  |  |  |  | **Evidence:** Lesson observations, planning documents, Learning walks, Staff feedback, PE action plan, PE lead performance management document.  **Sustainability**: Staff increased knowledge for future years.PE subject lead competency to strategically continue moving the school forward in terms of PE. House leaders in every class available to support colleagues to continue to move practice forward and model lessons/ team teach as needed. |
| **Links to whole school development plan: Development of leadership capacity throughout the school** | | | | | | |
|  | | | | | | |